## Guidelines
Object Point Estimation Model | [10 empty] | TPPPL02A Version 3.80
Guidelines
Step 1 : Assess object counts | Estimate Number of Screens, Reports, 3GL component ( programming language module) involved in developing application
Step 2: Assign complexity | Classify each object into " Simple", "Medium", " Complex" , " Highly complex "depending on values of characterstic dimension mentioned in table below
For Screens | [5 empty] | For Reports
| Number of Source Data Tables | [5 empty] | Number of Source Data Tables
No of Views contained | Total< 4 | Total< 8 | Total<10 | Total 10+ |  | No of Views contained | Total< 4 | Total< 8 | Total<15 | Total 15+
<3 | Simple | Simple | Medium | Medium |  | <3 | Simple | Simple | Medium | Medium
3 to 7 | Simple | Medium | Complex | Complex |  | 3 to 7 | Simple | Medium | Complex | Complex
8 to 14 | Medium | Complex | Complex | Highly Complex |  | 8 to 14 | Medium | Complex | Complex | Highly Complex
15 + | Complex | Highly Complex | Highly Complex | Highly Complex |  | 15+ | Complex | Highly Complex | Highly Complex | Highly Complex
Step 3: Assign complexity weight | The Numbers in each Cell is then weighed according to the table below.
Complexity weight for object points
Number of Source Data Tables
|  |  | Object type | Simple | Medium | Complex | Highly Complex
|  |  | Screen | 1 | 2 | 3 | 6
|  |  | Report | 2 | 5 | 8 | 16
|  |  | 3 GL component modules | 4 | 6 | 10 | 20
|  |  | 15 + | 8 | 12 | 18 | 24
Step 4: Determine object points | Determine all weighted object instances to get one number, Object point count ( consider % reuse )
Step 5: Determine productivity rate | Productivity = Number of object points / Person month
| Developer’s experience and capability |  |  | Very Low | Low | Nominal | High | Very High
| Maturity and capability |  |  | Very Low | Low | Nominal | High | Very High
| Productivity |  |  | 6 | 7 | 8 | 12 | 15
Step 6: Estimate | Estimate effort in person months - Number of object points / Productivity
Consideration:
This model was applied to two projects viz, iMitra Services and Essar Oil Mobile Learning project, considering a standard effort of 20 person hours to complete one object point. It was found to be in agreement within less than 10% variance. Thus It has been decided to take this estimation model for other projects. This model will be reviewed and re-calibrated after six months after collecting and analysing data from other projects.
Tailoring Guidelines
Based on the skill set and experience of the project team, the Project Manager can change the values of the parameters in cells F:31 to J:31

## Decomposition
Decompose the requirements in this page Page2/3 | [6 empty] | TPPPL02A Version 3.80
Complexity
Sl.No | Mobile LMS Web Portal Features | Sub-Feature | Operations | UI Screen | Reports | 3GL | 15+ | Remarks |  | Simple | Medium | Complex | Highly Complex
1 | Login |  |  | SIMPLE |  | SIMPLE |  |  | UI Screen | 7 | 11 | 2 | 1
2 | Logout |  |  | SIMPLE |  | SIMPLE |  |  | Reports | 1 | 7 | 1 | 1
3 | Change Password |  |  | SIMPLE |  | MEDIUM |  |  | 3GL | 3 | 19 | 5 | 1
4 | Forgot Password |  |  | SIMPLE |  | MEDIUM |  |  | 15+ | 1 | 1 | 1 | 1
5 | Management | User | Add, Edit, Delete, View | MEDIUM |  | MEDIUM
|  | Role & Privileges | Add, Edit, Delete, View | MEDIUM |  | MEDIUM
|  | Group | Add, Edit, Delete, View | MEDIUM |  | MEDIUM
|  | Department | Add, Edit, Delete, View | MEDIUM |  | MEDIUM
|  | Managers-Employees | Assign, Un-Assign | MEDIUM |  | MEDIUM
|  | Course | Content creation, Assign content, Content upload, Publish, Delete, Assign Location | COMPLEX |  | COMPLEX
6 | Reports | Employees List | Export as CSV file |  | MEDIUM | MEDIUM
|  | Users list for Assigned courses | Export as CSV file |  | MEDIUM | MEDIUM
|  | Users list for Completed Courses | Export as CSV file |  | MEDIUM | MEDIUM
|  | List of Public courses | Export as CSV file |  | MEDIUM | MEDIUM
|  | Course wise list of users | Export as CSV file |  | MEDIUM | MEDIUM
|  | List of Employees reporting to a selected manager | Export as CSV file |  | MEDIUM | MEDIUM
7 | Help | Frequently Asked Questions |  | SIMPLE |  | MEDIUM
8 | Upload users | Bulk upload of users | Spreadsheet format | SIMPLE |  | MEDIUM
9 | Notification | Push Notification |  | MEDIUM |  | MEDIUM
|  | In App Notification |  | MEDIUM |  | MEDIUM
10 | Reward & Recognition |  |  | MEDIUM |  | COMPLEX
11 | Learning Certificates |  |  | MEDIUM |  | MEDIUM
12 | Contests |  |  | MEDIUM |  | COMPLEX
13 | Database Tables (if additionally required) | CRUD Operations |  |  |  | COMPLEX
14 |  | AAA |  | SIMPLE | SIMPLE | SIMPLE | SIMPLE
|  | BBB |  | Medium | Medium | Medium | Medium
|  | CCC |  | Complex | Complex | Complex | Complex
|  | DDD |  | Highly Complex | Highly Complex | Highly Complex | Highly Complex
If you need additional rows, please insert rows above this row!!!

## Estimation Work sheet (hidden)
Estimation Work Sheet
[8 empty] | PDLC Phases | % of Total Effort | Total Effort in person days
|  | Simple | Medium | Complex | Highly complex |  |  | Analysis | 8 | 71.28
| Screens | 7 | 11 | 2 | 1 |  |  | Design | 12 | 106.92
[8 empty] | CUT | 44 | 392.04
| Reports | 1 | 7 | 1 | 1 |  |  | IT & Regression testing | 26 | 231.66
[8 empty] | CM & release Management | 2 | 17.82
| Business Logic | 3 | 19 | 5 | 1 |  |  | Project Management & SQA | 8 | 71.28
[8 empty] | Total | 100 | 891
| 15+ | 1 | 1 | 1 | 1
| Object points | 360 |  | % Reuse | 10 |  |  | In Hours |  | 7128
| Total Object points | 324
| Effort in person month | 40.5 | Effort in Person Days |  | 810 | Buffer % | 10
| Overall Effort in Person days | 891

## Effort
|  | Estimation Worksheet for Development Project Page 3/3 |  |  |  |  | TPPPL02A Version 3.80
This print out may not be the latest version, if it is not stamped as “Master Copy” or “Controlled Copy
Customer: |  |  |  | Project:
Estimation type |  | Detail Estimation
1. Project Size
Project Size |  |  |  | 360 | Object Points
|  | Reusable Components |  | 10 | %
|  | Total effective Object Point |  | 324
2. Project Effort
|  | Person Hours |  | 7128
|  | Person Days |  | 891 |  | Buffer | 10 | %
|  | Person Months |  | 40.5
2.1 Estimates for Entire Life-cycle
Major Activities |  |  | Total Effort in pd |  | Resource Loading | Schedule in days | Remarks
2.1.a Requirement Phase |  |  | 18 |  | 3 | 6
2.1.b Analysis and Design Phase |  |  | 294 |  | 4 | 73.5
2.1.c Development Phase |  |  | 223
2.1.d Testing Phase |  |  | 223
2.1.e Delivery Phase |  |  | 27
2.1.f Project Management |  |  | 107
Total Effort (Person days) |  |  | 892 |  |  | 79.5 | 18.3462 | weeks
3. SCHEDULE & TEAM SIZE
3.1 IF SCHEDULE IS FIXED : To find the Average Team Size. |  |  |  |  | Applicable? (Yes / No)
|  | Enter schedule (in weeks) |  | Weeks
|  | Average Team Size |  | Persons
3.2 IF AVERAGE TEAM SIZE IS FIXED : To find the project duration. |  |  |  |  | Applicable? (Yes / No)
|  | Average Team Size | 6 | Persons
|  | Optimum Elapsed time | 29.7 | Weeks
|  | Suggested Minimum Elapsed Time | 22.275 | Weeks
Prepared By: |  | abc |  |  | Date: | 2016-12-03
Review Comments | no comments
Reviewed By: |  | xyz |  |  | Date: | 2016-12-03